AL-506 Tuscaloosa City and County

FY2025 Continuum of Care (CoC) Competition

Timeline and Deadlines

TIMELINE AND DEADLINES

| Date | Activities |
| --- | --- |
| January 09, 2024 | FY2025 CoC Program Registration |
| March 7, 2024 | FY2025 CoC Program Registration Deadline |
| June 26, 2024 | HUD Released Grant inventory Worksheets (GIW) |
| July 17, 2024 | Grant Inventory Worksheets Due |
| July 19, 2024 | Ranking and Review Committee Selection |
| November, 13, 2025 | HUD NOFO Released |
| November 14, 2025 | HUD NOFO Announcement emails sent to CoC |
| November 14, 2025 | Publish NOFO Announcement to City website. |
| November 21, 2025 | Timeline Emailed to CoC Board for Vote |
| November 24, 2025 | Publish timeline to City of Tuscaloosa website |
| *TBD* | Project Applications Available in E-Snaps |
| December 4, 2025 | WACH CoC General Meeting |
| December 8, 2025 | Intent to Reapply Published *due for all renewal projects |
| December 8, 2025 | Notice of Intent Published *for all new projects |
| December 12, 2025 | Deadline: Renewal Project Applications submitted in e‐snaps |
| December 12, 2025 | Deadline: New Project Applications submitted in e‐snaps |
| December 15, 2025 | CoC Notification to Project Applicants |
| December 15, 2025 | The Review and Rank Committee will begin reviewing applications. |
| December 23, 2025 | Executive Committee notifies applicants of the project status and ranking (Accepted/Rejected) |
| December 29, 2025 | Deadline for Appeal Submissions of Review and Rank Decision |
| December 30, 2025 | Public Posting: R&R releases ranking results to Board and to public |
| January 7, 2026 | Public Posting: CoC Application, Attachments, Priority Listing |
| January 14, 2026 | Deadline for FY2025 Application Submission to HUD |