AL-506 Tuscaloosa City and County

FY2026 Continuum of Care (CoC) Competition

Timeline and Deadlines

TIMELINE AND DEADLINES

| Date | Activities |
| --- | --- |
| May 4, 2026 | FY2026 CoC Program Registration |
| June 1, 2026 | HUD NOFO Released |
| June 3, 2026 | HUD NOFO Announcement emails sent to CoC |
| June 3, 2026 | Publish NOFO Announcement to City website |
| June 8, 2026 | Executive Committee Meeting |
| June 22, 2026 | HUD Released Grant inventory Worksheets (GIW) |
| June 29, 2026 | Grant Inventory Worksheets Due |
| June 30, 2026 | FY2026 CoC Program Registration Deadline |
| June 30, 2026 | FY2026 CoC Program Review Deadline |
| *TBD* | Project Applications Available in E-Snaps |
| July 2, 2026 | Timeline Emailed to CoC Board for Vote |
| July 6, 2026 | Publish timeline to City of Tuscaloosa website |
| July 6, 2026 | HUD Final Released Grant Inventory Worksheet (GIW) |
| July 10, 2026 | Intent to Reapply Published *due for all renewal projects |
| July 10, 2026 | Notice of Intent Published *for all new projects (Projects should be identified in the notice) |
| July 13, 2026 | Request Certification of Consistency with Con Plan |
| July 16, 2026 | WACH CoC General Meeting |
| July 24, 2026 | Deadline: Renewal Project Applications submitted in E-SNAPS |
| July 24, 2026 | Deadline: New Project Applications submitted in E-SNAPS |
| July 27, 2026 | The Review and Rank Committee will begin reviewing applications. |
| July 31, 2026 | Executive Committee notifies applicants of the project status and ranking (Accepted/Rejected) |
| August 5, 2026 | Deadline for Appeal Submissions of Review and Rank Decision |
| August 7, 2026 | Public Posting: R&R releases ranking results to Board and to public |
| August 21, 2026 | Public Posting: CoC Application, Attachments, Priority Listing |
| August 21, 2026 | Intent to submit CoC Application |
| August 26, 2026 | Deadline for FY2026 Application Submission to HUD |